EVALUATION OF THE PROJECT

# 2 Objectives of Evaluation

The evaluation of the project has been carried out for following three main activities of the project:

* Generating awareness, sensitization of stakeholders, rapid visual survey (RVS) trainings, mass casualty Management in schools and hospitals and capacity building of various stakeholders including State and district Level Nodal Officers from State Governments, Public Sector Organizations and all related line departments.
* Capacity development trainings on Incident Response System, Table Top & Mock exercises to sensitize officers/stakeholders across the eight North Eastern States namely states Assam, Arunachal Pradesh, Manipur, Mizoram, Meghalaya, Nagaland, Sikkim and Tripura
* Assessment of the multistate earthquake disaster preparedness and to evolve the coordinated evaluation of SDMAs and NDMA

## 2.1 Methodology Adopted for Evaluation

The following methodology was adopted by IIPA to evaluate the activities undertaken by CSIR-NEIST *on site* visit of Assam , Sikkim , Agartala and Imphal was conducted by Prof. Vinod K. Sharma and Dr. Shyamli Singh Project Director(s) for evaluation of the project “M 8.7 Shillong 1897 Earthquake Scenario: NE Multi –State Preparedness Campaign”. They interacted with the stakeholders involved in the different activities *viz.* CDP, RVS, IRS trainings, Mock drills, workshops, meetings etc. The methodology followed for evaluation is as follows:

**Figure 2.1: Evaluation methodology adopted by IIPA**

### 2.1.1 Evaluation of project

This evaluation is based on well-established evaluation criteria as set out below (Methodological Framework for Evaluation) with the consultation of earthquake experts:

* Methodology used by CSIR-NEIST
* Relevance of the project with respect to capacity building and awareness generation
* Progress of the project and total outcome
* Fund utilization
* Over-all gain from the project

### 2.1.2 Evaluation outcome

After the preliminary survey, consultative discussions were done and the parameters for evaluation were developed. Based on the evaluation indicators/ criteria, a Google form attached as (Annexure I) was developed and designed to get the feedback of the stakeholders who had participated in the different programs organized under this project e.g CDP, RVS, School Sensitization Workshop or other earthquake awareness and disaster preparedness activities organized. The emails were circulated in the first week of April and the participants were also telephonically informed about the evaluation and the procedure to fill up the form. The stakeholders were also given reminder mails and calls for submitting the forms (Annexure V).

Analyses of the responses facilitated in understanding the impact of these training, programs and workshops on the stakeholders and identify the gaps and help in formulating a strategy for disaster preparedness and mitigation in the NE states.

## 2.3 Timeline and Deliverables

The duration of evaluation was for a period of 3 months starting from the month of February 2016 to May, 2016. The activities undertaken by IIPA after the signing of the MoU is summarized below the Gantt chart.

**Figure 2.2: Gantt chart of the Activities conducted**